## M&Eplan_retrofitted logframe
| Results Hierarchy |  | Indicator | TARGETS |  |  |  |  | Description/Definition
|  |  |  | Baseline | Phase 11 | Interim | End of Project | Description/ Definition (3) |  | COI Alignment (for internal reference only) | How to Measure/Count (internal) | Raw Data Required | Unit of Measurement | Data Sources (6) | Data Collection Methods | Type of Data Analysis | Data Collection Frequency | Responsibility (Data Collection) | Users | Use of Information
Goal
| Contribute to the reduction of poverty incidence in target areas through sustainably increased income of small farmers and unemployed rural women and men across selected agri-based value chains |  | Number of municipalities with poverty rates above 40% in target areas reduced | 349 |  | 320 | 260 |  | PSA definition and methodology of determining the poverty level of cities and municipalities in the Philippines or the small area estimates. |  |  | Poverty Incidence among Families (%) Poverty Magnitude per municipality | Level of poverty in cities and municipalities | PSA City and Municipal Level Poverty Estimates(annual) | Survey/Study | Quantitative Data; Qualitative Data | Interim & End-of-Project Reviews | NPCO | National Government Agencies: DA,DAR, DTI, NEDA & other agencies Development Partners: Bilateral and multilateral development agencies Policymakers and researchers | Impact evaluation or post-project evaluation Formulation of national policies, programs and projects on agriculture value chain development
Development Objective
| Provide enabling conditions for the sustained growth of small and micro enterprises in selected agricultural commodity chains with comparative advantages, market demand, growth potential, links to small farmers and the potential for job creation. |  | 78,000 project-supported HHs with increase in income by at least 60% from on and off farm activities | 2000 |  | 25000 2 | 78000 | - Project supported Farming HHs are members of FOs who are part of the DIPs; and those who receive interventions through the RAPID Project. - Farming Households amembers of FOs identified in the DIPs - On and off farm activities refer to all activities within the Value Chain ; - | - Project supported Farming HHs with increased income of 60%. Farming HHs are defined as those : 1. involved in the agricultural value chain within the four commodity sectors identified by the project; 2. receiving interventions/benefits from the project ; 3. active member of FOs (in the DIPs) within the project provinces; 4. actual landowner and/or actual tiller 5. able to provide cash or non-cash counterpart 6. may also include individual farmers who are part of the DIPs but may not be members of the FOs -The farmers should belong to the following priority commodities of the RAPID Project : 1. coffee, 2. cacao, 3. coconut, 4. Processed Fruits and Nuts -" On-farm income is generated from farming and agricultural production, including casual and seasonal labor. From the value chain lens, on-farm work occurs at the “beginning” of the value chain, increasing household productivity, reducing post-harvest losses (at the farm level), strengthening or creating producers associations, etc.. -"Off-farm income encompasses all agriculture-related income opportunities beyond the farm. From the value chain lens, off-farm income includes the “middle” and “end” of the value chain as agricultural goods leave the farm to ultimately reach the consumer. Examples of off- farm income and enterprise include extension services, processing, packaging, storage, and transportation." | 1.2.4 Households reporting an increase in production. 1.2.7 Partner financial service providers with operational self-sufficiency above 100% 2.2.5 Rural producers' organizations reporting an increase in sales Updated the definition of Farming HHs based on the discussion during the M&E Technical Session On-farm and off-farm definition source: USAID Office of Food for Peace. (2016): https://www.fsnnetwork.org/sites/default/files/SCALE%20Glossary%20Final_online%20508.pdf | Compute the farmer's annual gross income for the past 12 months , specific to the commodity assisted through the Project, and determine its percentage increase vis-à-vis baseline value . ( Annual Gross Income during survey/ baseline value) X 100% Annual Gross Sales less Cost of Sales | Annual gross income or net receipts (Annual Gross Sales - Cost of Sales ) of project beneficiaries from commodities supported through the Project | Annual Gross Income or Net Receipts in Php | Annual outcome Survey (AOS) Results/Study; | Survey Focus group discussions Year-end reviews | Qualitative and Quantitative | Baseline, Midterm & End-of-Project or Completion | NPCO, PCU, RCUs | National Government Agencies: DA,DAR, DTI, NEDA & other agencies Development Partners: Bilateral and multilateral development agencies Policymakers and researchers | Impact evaluation or post-project evaluation Formulation of national policies, programs and projects on agriculture value chain development
|  |  | 36,000 incremental jobs generated on farm and in project-supported MSMEs, 40% for women | 0 |  | 10000 | 36000 | Jobs (count the number of jobs and number of workers employed) refer to paid work and if unpaid - it has to be monetized | Number of new full-time or recurrent seasonal on-farm and off-farm, paid and unpaid jobs created since project start-up, either as independent individuals (self-employed) or as employees of micro, small and medium-sized enterprises and Farmer Oganizations MSMEs - with business activity or enterprise engaged in industry, agribusiness and/or services, whether single proprietorship, cooperative, partnership or corporation, categorized based on the following asset size: (i) Micro: not more than Php 3,000,000; (ii) Small : Php 3,000,001 – 15,000,000; (iii) Medium: Php 15,000,001 – P1000,000,000 MSMEs assisted in the Project through the RAPID interventions (i.e., market brokering sessions, trade fairs, and etc.). They are engaged based on the following criteria: (i) Micro Enterprises (ME), Small Enterprises (SE), and Medium enterprises (MEs) privately or collectively owned, expanding services to value chain stakeholders; (ii) with valid business license; (iii) Latest Annual Tax Return; (iv) Part of the DIPs; (v) MSMEs not part of the DIPs may also be considered provided that they have received initial project interventions and are part of the existing value chains (vi) Engaged/involved in one or more Agri-VC functions (project's priority commodities); (v) Able to provide equity; (vi) FOs (associations and cooperatives) can be considered as MSMEs if they engage in an enterprise but should be registered (e,g SEC, CBA) Farmer Organizations in the Project are engaged based on the following criteria: (i) w/ Valid certification of registration (CDA/ SEC/ DOLE); (ii) w/ Business License if engaged in business; (iii) w/ at least 2 years in operations; (iv) Part of the DIPs; (v) Able to provide equity | (2.2.1): Number of new jobs created: defined as Refers to the part-time and full-time jobs generated by the WMEs. Full-time employees render a total of eight hours per day while part-time employees render less than eight hours. | Collect sex-disaggregated data of new employed workers of MSMEs and FOs since the start of the Project's support to beneficiaries until the moment of the survey (# of employed women workers/ total number of new jobs) X 100% Count the number of new jobs created since the start of Project's support to the beneficiaries until the moment of survey FOs who are also operating as MSMEs (those who qualified the criteria) are also counted as MSMEs Refer to PSA definition of employed persons: "Include all persons 15 years old and over as of their last birthday and during the basic survey reference period are reported as either: a. At work. Those who do any work even for one hour during the reference period for pay or profit, or work without pay on the farm or business enterprise operated by a member of the same household related by blood, marriage, or adoption; OR b. With a job but not at work. Those who have a job or business but are not at work because of temporary illness/injury, vacation, or other reasons. Likewise, persons who expect to report for work or to start operation of a farm or business enterprise within two weeks from the date of the enumerator's visit, are considered employed." | - List/inventory of paid & unpaid full time and seasonal workers of MSMEs and FOs disaggregated as women, youth, IP and youth | Number of total full and part-time workers employed | PSA Annual Labor Market Statistics Value Chain Stakeholder Profile Annual Outcome Survey/Study | Survey Focus group discussions | Qualitative and Quantitative | Baseline, Midterm & End-of-Project or Completion | NPCO , RCUs, PCUs | National Government Agencies: DA,DAR, DTI, NEDA & other agencies Development Partners: Bilateral and multilateral development agencies Policymakers and researchers | Impact evaluation or post-project evaluation Formulation of national policies, programs and projects on agriculture value chain development
|  |  | 1,050 MSMEs reported increase in profit |  |  | 710 | 1050 |  | Number of project-supported MSMEs and FOs surveyed reporting an increase in profit, as shown by sales, income and expenditure patterns. | 2.2.2: Percentage of supported rural enterprises reporting an increase in profit | Net receipts is estimated by deducting all expenditures and recurrent costs from total receipts per assisted MSME and FO. Refer to online percent change calculator: http://www.percent-change.com to compute percentage increase. | - Annual Expenditures and Recurrrent Costs ; - Annual Income or Sales; - Profit at the time of the survey - Number of MSMEs | Annual Profit in Php; % increase in profit # of MSMEs | Project's Profiling System Annual Outcome Survey (AOS) Results | Survey (AOS) , Focus group discussions, Year-end reviews | Qualitative and Quantitative | Baseline, midterm and end-of-project or completion | NPCO / RCU/ PCU | National Government Agencies: DA,DAR, DTI, NEDA & other agencies Development Partners: Bilateral and multilateral development agencies Policymakers and researchers | Impact evaluation or post-project evaluation Formulation of national policies, programs and projects on agriculture value chain development
Outcome 1:
1 | Outcome 1: Producers and value chain actors execute collaborative action plans and build commercial partnerships in selected commodity chains | 1.a | Percentage increase in value of sales of participating MSMEs, Farmers Associations and Cooperatives | TBD |  | (+)30% | (+)100% | This indicator refers to the reported number of MSMEs who have an increase in value of sales resulted from the participation in investment planning and commercial partnerships in project's priority commodity chains. Value of sales will also be monitored periodically. | MSMEs/Farmers/FAs/FOs who have recorded an increase in the volume of production sold or in the value of sales compared to the preceeding year, resulting from the participation in the project's investment planning, commercial partnerships, and project's inteventions | 2.2.5: Number/ Percentage of rural producers’ organizations reporting an increase in sales 1.2.4 Households reporting an increase in production | Collect data on the total sales of MSMEs/Farmers/FAs/FOs ' priority products for the year. Compare the present value with previous record and use the online percentage calculator: http://www.percent-change.com to get the percentage change. To get the actual value for the indicator, count the number of MSMEs/ Farmers/ FAs/FOs whose sales has increased by at least 30% by mid-term and 100% | Annual Sales per MSME /Farmers/FAs/FOs; Percentage of sales increase of MSMEs, FAs, FOs | Annual Sales in Php; | Annual outcome results; MSMEs' income statements and sales inventory Tracking Forms | Annual Outcome Survey, Interviews/Survey FGDs Administrative reporting | Quantitative (descriptive or inferential) and qualitative analyses | Baseline, annual and end-of-project | NPCO (AOS Service Provider)/ RCU/ PCU | DTI / Implementing Units, IFAD , LGUs, NEDA, DA , other project partners | Impact evaluation or post-project evaluation Formulation of national policies, programs and projects on agriculture value chain development
|  | 1.b | No. of commercial partnerships developed between farmers cooperatives and SMEs/large corporations |  | 4 | 100 | 100 | Refer to signed CPAs between the anchor firms and FOs/FAs | Refers to implemented signed Commercial Partnership Agreements (CPAs) between the anchor firms/MSMEs and FOs/FAs based on approved DIPS. Implemented pertain to fulfilled agreements and commitments of signed CPAs between anchor firms and FOs | COI: 2.2.3 Rural producers organizations engaged in formal partnerships/agreements or contracts with public or private entities defined as: Refers to the number/ percentage of surveyed producers’ organizations that have established contractual or other types of arrangements with other value chain stakeholders and/or public entities, with project support. Includes upstream and downstream arrangements (e.g. input provision or selling arrangements) and partnerships with public and/or private entities. | Collect data on signed CPAs between anchor firms and FOs/FAs | List of Anchor Firms and FAs/FOs* per signed CPAs; List of approved DIPs aligned with the signed CPAs; List/details of of interventions/agreements fulfilled based on the signed CPAs *Farmers’ Associations/ Cooperatives: No. of farmers participated disaggregate by Sex, Age Group, Indigenous Peoples, Household headed by Women, industry cluster, and value chain activity SME: Asset Size, Industry Cluster, value chain activity | Number of Anchor Firms, FOs Number of CPAs; Number of interventions/ agreements; Number of beneficiaries disaggregated according to men, women, IP and youth | Copy of signed and notarized CPAs; Detailed Investment Plans (DIPs); Project Progress Reports; CPA, DIP/Matching Grant Agreement Implementation Tracking/Data Capture Forms | Annual Outcome Survey, Interviews/Survey FGDs Project Reporting | Quantitative and Qualtitative Data; | Baseline Annual Completion | NPCO, RCUs, PCUS | DTI / Implementing Units, IFAD , LGUs, NEDA, DA , other project partners | Analysis for the project outreach and project effectiveness and impact
Outputs:
| Networks of Negosyo Centers in target provinces serving as one stop shop to promote entrepreneurship established | 1.1.a | Number of networks of Negosyo Centers set up servicing farmers, farmers associations, cooperatives and MSMEs in 21 provinces | 0 | 4 | 10 | 21 | This refers to the Provincial Negosyo Centers being set up as an entry point for the delivery of RAPID Growth project services in the Province. These provincial-level NCs, in collaboration with the PCUs, will (i) identifying MSMEs interested in partnering with farmers; (ii) facilitating the preparation and monitoring of SIPs; (iii) facilitating and coordinating the participation of service providers; (v) ensuring the M&E of all project activities in the province, including the preparation of provincial AWPBs; and (v) liaising with value chain players and their councils and associations. | This refers to the Negosyo Centers being set up at the provincial level as entry point for the delivery of RAPID Growth project services to project beneficiaries in the target provinces. The NCs facilitate the exchange and sharing of information, business referral and the ease of coordination in the RAPID project implementation. The NC network acts as one-stop shops facilitating the access of farmers, cooperatives and MSMEs to a range of business and financial services to be provided by the project. | TOR of NCs Old PIM definition: This refers to the Provincial Negosyo Centers being set up as an entry point for the delivery of RAPID Growth project services in the Province. These provincial-level NCs, in collaboration with the PCUs, will (i) identifying MSMEs interested in partnering with farmers; (ii) facilitating the preparation and monitoring of SIPs; (iii) facilitating and coordinating the participation of service providers; (v) ensuring the M&E of all project activities in the province, including the preparation of provincial AWPBs; and (v) liaising with value chain players and their councils and associations. | Collect data on: 1. NCs set up per province; 2. Disaggregated (sex and focus group) Project beneficiaries assisted through NCs (E-CPMS of NCs could be utilized) 3. Information on assistance provided (date and type) | List of Negosyo Centers in project sites assisting project beneficiaries List and number of of FHHs, farmers, MSMEs assisted/supported in NCs (disaggregated as men, women, youth, IP). List of MSMEs disaggregated by asset size | Number of NCs; Number of FAs, Coops, MSMEs assisted | Progress Reports NC's E-CPMS Form 10-Negosyo Center Tracker | Project Reporting | Quantative | Quarterly | Negosyo Centers, RCUs, PCUs | DTI, NPCO, VC Stakeholders | Analysis of Project outreach; Information shall contribute in assessing effectiveness of NCs as a support mechanism in the implementation and delivery of services and assistance to project benefiiciaries.
1.1 |  | 1.1.b | Number of FAs/coops served |  |  | 180 | 300
|  | 1.1.c | Number of MSMEs served |  |  | 450 | 750
1.2 | Qualified business providers able to provide business services to MSEs | 1.2.a | Number of pool of qualified service providers set up per province | TBD | 8 | 8 | 21 | This refers to the number and inventory of qualified service providers that will be engaged in delivering services to the target groups. They will be pooled per province and according to their field of expertise. Accreditation of BDS providers will be the means of verification for this specific indicator. | This refers to individuals and groups (institutions, firms) of business development service providers (i.e. Extension Services Providers), engaged in delivering DIP-based services / capbuild interventions aligned with the Project's Competency-Based Capacity Development Framework (CBCDF) and Extension Services Framework. | OLD PIM definition: This refers to the number and inventory of qualified service providers that will be engaged in delivering services to the target groups. They will be pooled per province and according to their field of expertise. Accreditation of BDS providers will be the means of verification for this specific indicator. | Collect data on number of groups/organizations of service providers per province who are officially engaged* and have conducted capbuild interventions with the Project's direct beneficiaries *qualified based on the project's selection criteria and succeeded in procurement process/ with signed contract | 1. Inventory/list of qualified Services Providers (names/organizations, disaggregated ) based on their location and competencies/expertise (agricultural enterprise, agricultural value chain development, livelihoods, agro-enterprise development, agribusiness, value chain finance or agricultural finance) responding to capbuild needs/support of Project's partner beneficiaries per industry; 2.Details of Trainings/services (date, name of SP/Resource Person, venue, Participants) interventions/capbuild provided to Project beneficiaries | Number of Service Providers; Number of trainings/capbuild/ services | Signed Contracts/MOA of Service Providers and Terms of Reference; Activity Documentations/Reports of Trainings Form 3-BDSP Registry | Project Reporting, Process Documentations | Quantitative | Quarterly | NPCO (BSO) , RCUs, PCUs, Service Providers | RCUs, PCUs, VC Stakeholders (FOs, Anchor Firms) | Ensure engagement of qualified resource persons for the project's capdev/extension services that shall deliver quality trainings and services to project beneficiaries
| Capacities of farmers, farmers’ organizations and MEs to manage enterprises strengthened | 1.3.a | number of farmers trained, disaggregated as men, women, IP and youth |  |  | 45000 | 78000 |  | This refers to the number of Farmer’s Associations, cooperatives, and MSMEs who were provided various capacity building activities* related to enterprise strengthening. The Project will also monitor the results of these capacity building provision by tracking those FAs, cooperatives, and MSMEs on how the acquired knowledge may have influence changes on their respective activities in the value chain. * FOs: Organizational Entrepreneurial, Governance, Organizational Managment, Institutional Marketing Management, Human Resource Management, Financial Management, Networking and Linkage-Building; MSMEs: Entrepreneurial Competency, Management, Marketing Management, Human Resource Management, Financial Management, Networking and Linkage Building Farmers: Managing Natural Resources, Managing Finances, Marketing, Teamwork | COIS: 1.1.17 Persons in rural areas trained in financial literacy and/or use of financial products and services Definition based on old PIM defined as: This refers to the number of Farmer’s Associations, cooperatives, and MSMEs who were provided various capacity building activities related to enterprise strengthening. The Project will also monitor the results of these capacity building provision by tracking those FAs, cooperatives, and MSMEs on how the acquired knowledge may have influence changes on their respective activities in the value chain. *based on Competency-Based Development Framework | Gather data on the number of participants from staff who received/participated in capacity development trainings/activities on value chain development. Administer pre and post tests per activity. Compute the difference of the total scores of both tests (Deduct Post -test from pre-test results) to determine the number of participants with increased knowledge and skills. Refer to online percent change calculator: http://www.percent-change.com to compute percentage increase. | Number of beneficiaries disaggregated as type of beneficiaries (MSMEs, FOs, Smallholder Farming Households), men, women, IP, youth, and PWD Trainings/Activities conducted (title, date, venue, output, service provider) Pre and Post-test results |  | Activity Pre and Post-Tests; Activity Documentation/Reports; Form 4-Capbuild for Beneficiaries Tracker; Progress/Narrative Reports; | Project Progress Reporting (Documents and records), Surveys , Interviews | Quantitative | Quarterly | PCU, RCU, NPCO | DTI, NCs, NEDA, IFAD | To determine level of effectiveness and quality of project's capdev/interventions to Project beneficiaries. Results will be basis in identifying more effective support in improving capacities of project beneficiaries in managing and scaling up their enterprises. Ensure participation of relevant target groups and monitor the application of learnings
1.3 |  | 1..3.b | Number of FAs/cooperatives trained |  |  | 180 | 300
|  | 1.3.c | Number of MEs trained |  |  | 408 | 750
1.4 | DIPs connecting farmers to SMEs and facilitating access to markets and services | 1.4.a | Number of Detailed Investment Plans (DIPs) developed | 0 |  | 50 | 50 | Refers to the number of farming households who are identified in the DIPs that are endorsed by RTWG and signed by RD as approving authority | Pertains to DIP per commodity and province prepared by the Implementing Units that are endorsed by DIP-Regional Technical Working Group (RTWG) and signed by Regional Directors (RD) as approving authority | definition based on the agreements during the Technical Session in butuan City | Collect data on the number of farming households/ members of FOs in approved DIPs | Number of farming households per DIP disaggregated per focus group (PWD, sex, Youth, IPs) in the DIPs per commodity and province | Number of Farming Households Number of endorsed DIPs | DIPs endorsed by the RTWG and signed by RD as approving authority Form 1_DIP Preparation and Approval Tracker | Project Reporting, Process Documenting | Quantitative Data | Quarterly | NPCO, RCUs, PCUs | DTI, Implementing Units, IFAD, NEDA (RCUs, PCUs, Agency Partners) | Analysis on the collaborative partnerships and ensure involvement of Farming households
|  | 1.4.b | Number of farming households participate in Detailed Investment Plans (DIPs) | 0 | 5801 | 25000 | 78000 |  | Refers to the number of farming households who are identified in the DIPs that are endorsed by RTWG and signed by RD as approving authority | definition based on the agreements during the Technical Session in butuan City | Determine DIPs that were endorsed by RTWG and signed by RD as approving authority | Date of RTWG endorsement and RD approval; DIP details (anchor firms, commodity, number of FOs, productive investments, capbuild Reach of Farming Households) | Number of DIPs | Proceedings/Minutes of Meeting on the DIP Endorsement/ Approval Form 1_DIP Preparation and Approval Tracker | Monthly Project Reporting | Quantitative Data | Quarterly | NPCO, RCUs, PCUs
|  | 1.4.c | Number of partnership agreements entered into by FAs/ Coops, MSMEs or large enterprises |  | 4 | 100 | 100 |  | Refers to the signed CPAs between the anchor firms/MSMEs and FOs/FAs that were developed based on ongoing and approved DIPs. This will also include tracking the progress of the partnership on a regular basis which includes the assurance of both parties to conform with the terms and reference in the agreement. | Refers to the number of commercial partnership agreements signed between the farmers’ organization and SMEs. The project M & E will also include tracking the progress of the partnership on a regular basis which includes the assurance of both parties to conform with the terms and reference in the agreement. (Approved PIM as of September 2020) | Collect data on signed CPAs between anchor firms and FOs/FAs | Signed CPAs details on names anchor firms,MSMEs, name of partner FOs, Farmer Reach, Commodity/Industry, province, region Name of aligned DIPs | Number of CPAs, Number of anchor firms, Number of MSMEs, | Signed CPAs Progress Reporting Monthly Progress Report Form 2_CPA Tracker | Project Progress Reporting | Quantitative Data | Quarterly | PCU, RCU, NPCO
1.5 | Capacities of enablers (e.g., DTI, LGUs and industry councils) for value chain development strengthened | 1.5.a | Number of functional industry councils in selected value chain commodities |  |  | 24 | 24 |  | Pertains to the functional industry councils of priority commodities in target regions and provinces supported by and involved/engaged in the Project (e.g., DTI Industry Cluster Enhancement Program) providing support* to the Project/beneficiaries &recommendations/agreements/policy issuances aligned with/contributing to Project objectives and targets | Number of interagency bodies (RTWGs, ICs, etc) functional and providing support to beneficiaries (Approved PIM as of September 2020) | Gather: number of of industry councils provided with support/assistance (in any form of resource) and/or are engaged in the Project; and number of policies/directives supporting the industry councils/RAPID Project | # of Meetings/activities of Project-supported/participated Industry Councils; Policy recommendations/issuances | Number of meetings/ activities with industry councils; Number of policy issuances/agreements/recommendations | Minutes of meeting and resolutions passed Activity Documentation/ Activity Proceedings Meeting feedback (Client Satisfaction Feedback) Form 9_Enablers' Activity Tracker | Project Report Surveys, Interviews | Qualitative and Quantitative | Quarterly | PCU, RCU, NPCO, Partner industry councils/committees | Industry Councils/Committees (National, Regional, and Provincial), NEDA, DTI, VC Stakeholders, IFAD | Analysis on the institutional strengthening and ensure participation of relevant stakeholders. Basis for policy recommendations and industry initiatives that may be undertaken to strengthen exisiting industry councils/industries that shall support upscaling and sustainability of project beneficiaries
|  | 1.5.b | Number of DTI/NCs and LGUs Staff trained, disaggregated as men, women, IP, youth |  |  | 364 | 500 |  | Refers to the number of project staff/implementers and enablers trained on value chain development* under the Project and have recorded an increase in knowledge and skills * DTI RAPID Project Staff , NC Staff, LGU project staff, Agency Partners/Implementers **Core competencies that may be covered by the trainings/activities related to VC development identified in the Project's CBCDF: Understanding the Value Chain Approach, Understanding the Development Challenges of the Agriculture Sector, Facilitating Participative Processes, Incorporating Gender-sensitivity in Value Chains, Conducting Market Analysis |  | Collect data on the number of project staff who received/participated in capacity development trainings/activities on value chain development. Administer pre and post tests per activity. Compute the difference of the total scores of both tests (Deduct Post -test from pre-test results) to determine the number of participants with incerased knowledge and skills. Refer to online percent change calculator: http://www.percent-change.com to compute percentage increase. | Number of Project Staff Trained/partner implementers disaggregated as men, women, IP, youth, and PWD Trainings/Activities conducted with Project Staff (title, date, venue, output, service provider) Pre and Post-test results | Number of project staff/implementers Percentage increase in knowledge and skills | Activity Pre and Post-Tests; Activity Documentation/Reports; Capbuild Tracking Forms; Progress/Narrative Reports; Form 9_Enablers' Activity Tracker | Project Progress Reporting (Documents and records) , Surveys, Interviews | Quantitative | Quarterly | NPCO, RCU, PCU | DTI, NCs, NEDA, IFAD | Determine level of effectiveness and quality of project's capdev/interventions to Project implementers as basis in identifying more effective support to improve capacities of implementers in assisting project beneficiaries.
1.6 | Industry-based MIS providing information to stakeholders in the target value chains developed | 1.6.a | Number of industry-based MIS, accessible to value chain stakeholders, running and regularly updated | 0 |  | 3 | 3 | Number of MIS developed for the targeted value chains | Number of functional MIS developed for the targeted value chains (coffee, cacao, PFN, and coconut) Number of Knowledge Base/Hub per industry/sector/value chain integrated in the Project's Management Information System | Number of MIS developed for the targeted value chains. (Approved PIM as of September 2020) | Gather data on the number of MIS developed on the project's priority value chains/commodities based on the approved DIPs of the Project Gather data, information and knowledge stored in each Knowledge Base with the Project's Management Information System | VC-related report generated by the MIS | Number of MIS ﻿Number of Knowledge Bases | AWPB Progress Reports; VC-related data/information generated by MIS | Project Reporting ﻿Project Reporting and Profiling | Quantitative | Quarterly | NPCO (MIS team) | DTI, NPCO, RCU, PCUs, VC Stakeholders | ﻿Provide data analytics for data-driven and evidence-based decision-making
Outcome 2:
2 | Outcome 2:MSMEs secure the necessary access to producers, markets and suitable investment finance | 2.a | Number of Farming HH established linkage with markets, and availed financial services for productive investments | 0 | 1722 | 42000 | 70000 | This refers to the number of farming HHs, FOS/FAs, MSMEs (who are part of approved DIPs) who have accessed a financial product or service specifically promoted/supported by the project and its partner financial service provider (FSP), at least once during the past 12 months (annual reporting) or since project start-up (cumulative reporting). Such services include loans and micro-loans, saving funds, micro-insurance/insurance, remittances, and membership of a community-based financial organization (e.g. savings and loan group). MEs - Micro-entrepreneurs - Individual entity or a small cooperating enterprise with less than 3 Million Php asset size SMEs - Small (3-15 Million Php asset size ) and Medium Enterprises (Php 15.01 –100 M asset size) | This refers to the number of farming HHs, FOS/FAs, MSMEs who have accessed a financial product or service specifically promoted/supported by the project and its partner financial service provider (FSP), at least once during the past 12 months (annual reporting) or since project start-up (cumulative reporting). Such services include loans and micro-loans, saving funds, micro-insurance/insurance, remittances, and membership of a community-based financial organization (e.g. savings and loan group). | COI : 1.2.5 Households reporting using rural financial sevices: defined as: Refers to the proportion of beneficiary households interviewed who state that they are fully satisfied with and are using the financial products and services facilitated by the project, in order to invest in a productive or income-generating activity (i.e. as opposed to being used for consumption or other non-productive purposes). | Collect data of project beneficiariaries that have accessed/availed financial products or services through the project's partner FSPs; Determine proportion of beneficiary households interviewed who state that they are fully satisfied with and are using the financial products and services facilitated by the project, in order to invest in a productive or income-generating activity (i.e. as opposed to being used for consumption or other non-productive purposes). Identify beneficiary households interviewed who state that they are fully satisfied with and are using the financial products and services facilitated by the project, in order to invest in a productive or income-generating activity (i.e. as opposed to being used for consumption or other non-productive purposes). | List of Farmers from the FOs/ FAs/ Cooperatives, MSMEs disaggregated as men, women, IP, youth, asset size, etc; Financial Services that are availed from FSPs; Amount/type of services availed; | Number of participants/beneficiaries Number of financial services Number of financial services | Progress Reports; Matching Grant Agreements; Report of Participating Financing Institutions Annual Outcome Survey Results | Progress Reporting; Survey/Interviews; | Qualititative, Quantitative | Baseline Annual Completion | Partners FSPs, NPCO, RCU, PCU | DTI, IFAD, NEDA, VC Stakeholders | Analysis of project outreach and effectiveness of project interventions to beneficiaries Ensure participation of relevant target groups and monitor the application of learnings
|  | 2.b | Number of MSMEs established linkage with producers/farmers, markets, and availed financial services for productive investments | 0 | 8 | 710 | 1050 |  |  | 2.2.6 Households reporting improved physical access to markets, processing and storage facilities, defined as: Refers to the percentage of beneficiary households interviewed who claim that, as compared to the pre-project situation: (a) they can now more easily access the required market, processing or storage facilities; and that (b) these facilities are fully functional. Old PIM definition: This indicator refers to the number of farming households (participated during the preparation of RSIPs and DIPs) who have gained access and benefitting from the necessary markets and suitable finance. This refers to the number of MSMEs (participated during the preparation of RSIPs and DIPs) who have gained access and benefitting from the necessary producers and suitable finance. Reports on percentage increase in productivity of participating SMEs and Cooperatives will also be collected. Reports on percentage increase in volume of production at the farm level as well as percentage increase in the value of sales at the coop level will also be tracked.
|  | 2.c | % increase in productivity of participating SMEs and Cooperatives |  |  | 10% | 10% | Productivity formula= current - baseline/ baseline X 100 | Refers to the percentage of beneficiary households interviewed who claim that project-supported activities (e.g. training, input provision) have helped them increase their productivity compared to the previous year. Measures how well the resources are utilized by MSMEs/Farmers to produce output . | 1.2.4 (Number)Precentage of persons/households reporting an increase in production defined as: Refers to the percentage of beneficiary households interviewed (e.g. rain-fed and irrigated farms, livestock owners, fishers) who claim that project-supported activities (e.g. training, input provision) have helped them increase the quantity of key crops harvested as a result of better yields (i.e. quantity of crop harvested per unit of land area) or an increase in cropped area, compared to the previous year. For cereals, grain and legumes, production is normally measured in metric tons or kilograms. May also refer to an increase in livestock production (e.g. increased milk production, reduced animal mortality, improved fertility), or in the volume of fish catches as compared to the pre-project situation. Data collection methods | Productivity formula= output/inputs current - baseline/ baseline X 100 | Average volume of production (output); direct and indirect operational expense (input) | Metric tons; Expenses in Php | Financial Statements; Annual Outcome Survey Results | Financial Statements; Annual Outcome Survey | Quantitative, Qualitative | Baseline, Annual, Completion | NPCO, RCU, PCU
|  | 2.d | % increase in volume and value of sales at farm/coop level and SME level |  |  | 10% | 10% | MSMEs and FOs who have recorded an increase in the volume of production sold or in the value of sales compared to the preceding year, resulting from the participation in the project's investment planning, commercial partnerships, and project's inteventions | MSMEs and FOs who have recorded an increase in the volume of production sold or in the value of sales compared to the preceding year, resulting from the participation in the project's investment planning, commercial partnerships, and project's interventions. | 1.2.7 Partner financial service providers with portfolio-at-risk ≥30 days below 5%(1.2.6) | Roads in Kilometer Number of roads | Amount of Annual Sales per MSMEs, FOs, and Smallholder Farming Households | Annual sales in Php | Annual outcome results; MSMEs' income statements and sales inventory | Annual Outcome Survey, Interviews/Survey | Quantitative, Qualitative | Baseline, Annual, Completion | NPCO / RCU/ PCU
Outputs:
2.1 | Product of farmers, farmers’ organizations, cooperatives, SMEs conforming to market requirements enhanced | 2.1.a | 1.2.1.a Number of products form/types conformed to market requirements |  |  | 300 | 450 |  | Pertains to number of improved products resulting from project interventions* related to product development and market compliance. This also refer to the number of rural producers accessing or who recieved production inputs and/or technological packages / Conditional Matching Grants) from the Project to improve or enhance their level of productivity and achieve market conformities. *FOs: Operations & Technology and Product Development ; MSMEs: Operations, Technology and Product Development; Farmers: Innovation | 1.1.3 Rural producers accessing production inputs and/or technological packages Types of training based on Project's CBDF Old M&E Plan definition: This refers to the number of Farmer’s Associations, cooperatives, and MSMEs who have accessed the conditional matching grant to improve or enhance their level of productivity and achieve market conformities. | One product of partner beneficiary subjected to project intervention related to product development/market compliance = 1 count; Track service and individual count for the capdev; | # of improved/enhanced products #/name of beneficiaries assisted disaggregated as female, male, youth, PWD, IPs; Information of trainings/support (title, date, service providers,venue) provided to project beneficiaries | Number of products Number of beneficiaries assisted | AWPB Progress Report Form 6_Product Development & Consultancy Services Tracker | Progress Reporting AWPB Report | Quantitative Data | Quarterly | NPCO, RCU, PCUs | VC Stakeholders, DTI, NEDA, IFAD | Analysis of Project Outreach,
2.2 | Access to market | 2.2.a | Number of market linkages established |  |  | 150 | 250 |  | Refers to number of beneficiaries (Farmers, MSMEs, FOs) participated in/assisted through the Project's market development interventions* (market brokering sessions, trade fairs) |  | 1 MSME / (Group of Microprocessors) linked to market (bigger/institutional market) - 1 count; 1 FO linked to 1 market/MSMEs - 1 count; | # of beneficiaries assisted disaggregated as female, male, youth, PWD, IPs Information (title, date, service providers,venue) provided to project beneficiaries of regional, national, and international trade fairs and market brokering/networking sessions Trade Fairs Sales | Number of market linkages Amount of sales in Php | AWPB Progress Report Narrative Reports Trade Fairs Sales Report Form 7_Trade Promotion Services Tracker | Progress Reporting | Quantitative Data | Quarterly | NPCO, RCU, PCUs | VC Stakeholders, DTI, NEDA, IFAD | Analysis of Project outreach
2.3 | Financial Institutions (FIs) with improved capacities to serve target value chains players | 2.3.a | Number of FSPs extend innovative and 0 other value-chain financial services | 0 |  | 3 FSPs | 10 FSPs | Refers to FSPs that have received project support, either during the past 12 months (annual reporting) or since project start-up (cumulative reporting), to develop an outreach strategy, or to deliver products and services that are adapted to the needs and repayment capacities of the rural poor and other project beneficiaries. A new outreach strategy refers to any type of formalized plan for an FSP’s rural finance operations, including business plans or action plans to improve outreach and the inclusion of the rural poor. Other types of support to be considered include budget support, staff training, studies and technical assistance. Financial products and services include savings, credit, remittances and insurance. | "Refers to FSPs that have received project support, either during the past 12 months (annual reporting) or since project start-up (cumulative reporting), to develop an outreach strategy, or to deliver products and services that are adapted to the needs and repayment capacities of the rural poor and other project beneficiaries." "A new outreach strategy refers to any type of formalized plan for an FSP’s rural finance operations, including business plans or action plans to improve outreach and the inclusion of the rural poor. Other types of support to be considered include budget support, staff training, studies and technical assistance. Financial products and services include savings, credit, remittances and insurance." | Persons in rural areas accessing financial services | Collect data on the support provided to partner FSPs and their networks (in particular the type and date of support). FSPs should track the number of local branches and offices benefiting from this support and/or providing services to project target groups. 1 financial service provided per FSP to project beneficiaries = 1 count Names of project beneficiaries disaggregated as women, youth, IP, and PWDs. | Number of FSPs assisted by the Project; Data (date and type of financial products and services) on financial interventions and services provided per FSP; Number of and type beneficiaries assisted by FSPs (disaggregated as men, women, IP, women and youth ) | Number of FSPs Number of Financial Services Number of beneficiaries disaggregated as female, male, youth, PWD, IPs Amount of financial services in Php | FSPs Report; Reports of approved loans from FSPs as indicated in the MOU Matching Grants Agreements (MGAs) AWPB Reporting Form 5_Matching Grant Implementation Tracker Form 11_Equity Financing Tracker | Progress Reporting; | Quantitative | Quarterly | FSPs, PCUs, RCUs, NPCO | FSPs, VC Stakeholders, DTI, NEDA, IFAD | Determine the coverage of financial services and assess responsiveness of project's interventions to beneficiaries' financial needs
|  | 2.3.b | Number of suitable financial products developed |  |  | 5 | 10 |  |  | 1.1.6 Financial Service providers supported in delivering outreach strategis, financial products and sevices to rural areas
|  | 2.3.c | Number of linkages to financial services established |  |  | 250 | 350
|  | 2.3.d | Target number of enterprises benefitting from equity financing | 0 | 4 | 10 | 40 | Refers to the equiting financing provided by SBC Corp services | Refers to the financing support/assistance provided and extended by partner FSPs (e.g., SBC, and etc.)
2.4 | Farm-to-market infrastructure connecting production to market improved | 2.4.a | Length of farm-to-market road rehabilitated and maintained (in km) | 0 |  | 80 km | 140 km | The total length, in kilometres, of roads that have been fully constructed, rehabilitated or upgraded (e.g. from feeder road to asphalt road) by the project, either during the past 12 months (annual reporting) or since project start-up (cumulative reporting). All types of roads should be included, such as feeder, paved, primary, secondary or tertiary roads. Roads where construction/rehabilitation works have been started during the past 12 months but not yet completed, should not be reported. | The total length, in kilometres, of roads that have been fully constructed, rehabilitated or upgraded (e.g. from feeder road to asphalt road) by the project, either during the past 12 months (annual reporting) or since project start-up (cumulative reporting). All types of roads should be included, such as feeder, paved, primary, secondary or tertiary roads. Roads where construction/rehabilitation works have been started during the past 12 months but not yet completed, should not be reported. | 2.5 roads consutrcted, rehabilitated or upgraded | Collect data on : total length, in kilometres, of roads that have been fully constructed, rehabilitated or upgraded per FMI For each planned road or road segment, project records should include at least the following key data on the physical works: contract start and end date; number of kilometres of roads planned and actually constructed/rehabilitated/upgraded. To avoid double-counting, reporting should only cover the number of kilometres of roads where physical works have been fully completed during the past 12 months (even though works may have started earlier). Achievements linked to roads for which physical works have started during the past 12 months, but are not yet complete, will be reported in the next reporting period (or upon completion). | Roads rehabilitated in: - total length in kilometres - FMI information (area, number of reach, commodity, amount, contractor, contract start and end date) | Roads in Kilometer Number of roads | Completion Report/Progress Report Inventory Feasibility Studies submitted Detailed Engineering Design Program of works, LGU-MOA, Sub-project agreement, GeoTagging data Form 8_FMI Tracker | Progress Reporting; | Quantitative | Quarterly | DILG, LGUs, RCUs, PCUs | DTI, NEDA, VC Stakeholders, IFAD | Validation of project feasibility or investment returns analysis or economic analysis
1 phase 1 targets for government monitoring purposes; intended for 4 pilot provinces and clusters: Davao del Norte (Cacao); Bukidnon (Coffee); Agusan del Sur (Calamansi); and, Leyte (Coco coir)
2 Household covered for pilot phase; 1 HH per 2 hectares; 50 HH per cooperative; 10 HH per SME; 3 HH per micro enterprise
Note on F6: with 5801 targets in the original logfarme
Note on K6: '1.2.4 Households reporting an increase in production. defined as: Refers to the percentage of beneficiary households interviewed (e.g. rain-fed and irrigated farms, livestock owners, fishers) who claim that project-supported activities (e.g. training, input provision) have helped them increase the quantity of key crops harvested as a result of better yields (i.e. quantity of crop harvested per unit of land area) or an increase in cropped area, compared to the previous year. For cereals, grain and legumes, production is normally measured in metric tons or kilograms. May also refer to an increase in livestock production (e.g. increased milk production, reduced animal mortality, improved fertility), or in the volume of fish catches as compared to the pre-project situation. : Operational self-sufficiency (OSS) is a performance indicator denoting the sustainability of an FSP. It shows how well an FSP covers its costs with its operating revenue, and how reliant it is on donor funds. The higher the percentage, the stronger and more sustainable the FSP. A sustainable FSP should have an OSS index of over 100%, and preferably 120% or above. OSS is calculated using the following formula: Financial revenues (from the income statements) [Financial expenses + loan loss provision expenses + operating expenses] Community-based financial organizations that are not time-bound and are accumulating funds, should be required to calculate their OSS. The percentage of partner FSPs should be the proportion of partner FSPs in IFAD’s portfolio reporting an OSS of above 100%. 2.2.5 Rural producers' organizations reporting an increase in sales Refers to the percentage of producers’ organizations interviewed claiming that they have recorded an increase in the volume of production sold or in the value of sales compared to the preceding year, thanks to project marketing and other capacity-building support.
Note on J7: Based on the COIS indicator and definition (2.2.1): Number of new jobs created Refers to the part-time and full-time jobs generated by the WMEs. Full-time employees render a total of eight hours per day while part-time employees render less than eight hours. Included the definition of MSMEs and FOs based on the discussion during the technical session. Definition of MSMEs based on RA 9501 : Magna Carta for Micro, Small, Medium Enterprises
Note on L7: User:
Note on D8: Microsoft Office User:
Note on J8: definition is based on COI definition of profit under 2.2.2: Percentage of supported rural enterprises reporting an increase in profit FO is added in this definition
Note on L8: based on COI definition of profit under 2.2.2: Percentage of supported rural enterprises reporting an increase in profit
Note on D10: indicator in new logframe also cover FAs and Cooperatives in addition to MSMEs
Note on J10: Adopted COIS definition: 2.2.5: Number) Percentage of rural producers’ organizations reporting an increase in sales Added Farmers, FAs, and FOs as this was identified in the updated logframe
Note on F11: 4 phase 1 targets also reflected in the original logfarme
Note on J11: Proposing to use the term implemented instead of signed as this at the outcome level. Signed CPAs should be reflected at the output level
Note on M11: *based on old PIM definition
Note on F13: 4 targets also reflected in the original logframe
Note on J13: Reference: TOR of NC
Note on F16: 8 targets also reflected in the original logframe
Note on J16: Will the Project accredit BDS? how and what is the MOV for this? Define "set up" per province Definition based on old M&E Plan: This refers to the number and inventory of qualified service providers that will be engaged in delivering services to the target groups. They will be pooled per province and according to their field of expertise. Accreditation of BDS providers will be the means of verification for this specific indicator.
Note on L16: Selection Criteria based on the Extension Service Provicer Framework version ao 30 June 2022: Extensive experience in the fields of agricultural enterprise, agricultural value chain development, livelihoods, agro-enterprise development, agribusiness, value chain finance or agricultural finance; Experience in coffee, cacao, coconut and processed fruit and nuts value chains providing extension services an advantage Experience working in the target provinces an advantage Expertise in extension service development, delivery and in the implementation of programs for farmer groups, cooperatives, MEs or SME programs or projects providing services using various methodologies Knowledge of the various extension services approaches and models, including a general knowledge of the general situation and enabling environment (policy and regulatory) for Farmer’s Organization (Coop. Asso), MEs and SMEs Sound gender analysis skills as evidenced by prior experience with integrating gender in projects
Note on B17: Output 1.3 in updated logframe; strengthened is outcome level
Note on D20: same definitions as above
Note on J20: Farming Households that are part of the DIPs that are approved by the RTWG; or Farming HHs (part of the DIPs) that have received initial interventions through the Project
Note on F21: also reflected in the original logframe
Note on F22: this indicator and target is not reflected in the original logframe
Note on B23: "strengthened" in output statement not measured in the indicator; Proxy indicator/definition to measure this indicator (reflected under description/definition) : increased knowledge and skills
Note on D23: functional - outcome level results
Note on J23: In the March 2022 Mission, it was emphasized that for the Value Chain Governance, the RAPID Project complement the ICE Program at the regional and provincial levels. This was identified as the Project's entry point considering that the DTI-ICE Program is tasked to strengthen the industry councils.
Note on J25: Define the MIS stakeholders; Should we target different MIS per VC?
Note on F27: same phase 1 target also reflected in the original logframe
Note on L27: ba
Note on F28: 5 phase 1 targets are indicated in the original logframe
Note on F29: with 10% targets on the original logframe but not reflected in the retrofitted logframe
Note on F30: with 10% target in the original logframe but not included in the retrofitted logframe
Note on K32: COI definition: Refers to farmers, livestock owners or other rural producers who received support to access production inputs (e.g. chemical or organic fertilizers, pesticides, improved seeds, cattle or other animals, veterinary medicines, etc.) or technological packages (e.g. processing equipment, farming tools, animal health and artificial insemination kits, drip irrigation systems, etc.) thanks to project interventions. Such inputs or technological packages and options may be provided on a free basis, or against some beneficiary contribution. The capacity-building shall only concern primary production activities and it excludes training in processing, value addition, marketing or business development, which are being captured under SO2.
Note on J34: Definition based on on COI 1.1.6 1.1.6 Financial Service providers supported in delivering outreach strategis, financial products and sevices to rural areas
Note on F37: same 4 phase 1 targets are reflected in the original logframe
Note on L38: based on old definition in the PIM