## form8
PROFILE | [9 empty] | PROCUREMENT DETAILS |  |  |  |  | IMPLEMENTATION STATUS | [18 empty] | Remarks | FINANCIAL STATUS
BATCH | DIP Name | Name of FMR | Project Title | Municipality/ Province | Region | Length (km) | Commodity | Approved Budget Cost | Relative Weight (%) | ITB Posting | Opening of Bids | Date of NOA | Date of NTP (Received) | Name of Contractor | Contract Cost |  |  |  |  | Date Started | Contract Duration |  |  | Status | Actual Accomplishment (%) | % Slippage (delay/ahead) | Relative Weight (%) | Actual Length (kilometers) | Date of Completion |  |  | Date of Turnover | Date of Acceptance |  | Financial Accomplishment | Sub-Allotment Advice No. | Date Issued | Amount | Difference (Allotment - 95% of Contract Cost) | Date Issued | Amount | Date Issued | Amount | Date Issued | Amount | Balance
[15 empty] | IFAD Loan Proceeds (95% of ABC) | LGU Counterpart (5% of ABC) | Total Original Contract Cost | Total Revised Contract Cost | Reason of Revision |  | Original (cal. days) | Revised (cal. days) | Reason of Extension | [5 empty] | Target | Revised | Actual | [8 empty] | 1st Tranche |  | 2nd Tranche |  | 3rd/Final Tranche
Dropdown: Batch 1, 2, 3 and 4 | Dropdown data from DCF 1 |  |  |  | Data link from the DIP Name, to reflect the region of the selected DIP in column B. |  | Data link from the DIP Name, to reflect the commodity of the selected DIP in column B.